## Rencana Pengujian
Rencana Pengujian (Test Plan)
Deskripsi Perubahan | Handle pending transaction
Nomor PCR
Durasi Pengujian | 12th June 2023 to 13th June 2023
Lokasi Pengujian | Malaysia
Cakupan Pengujian
Wilayah Pengujian
Persyaratan Laporan
Strategi Pengujian | < Pengujian aplikasi/sistem untuk mencakup pengujian yang cukup baik dan pengecualian> • <Semua transaksi yang berhasil akan diizinkan untuk dilalui> • <Semua transaksi pengecualian tidak akan diizinkan untuk dilalui dan dilaporkan sebagaimana mestinya dalam laporan pengecualian> • <Skenario pengujian harus mencakup skenario positif dan negatif> • <Data uji harus mencakup data yang valid dan tidak valid> • <Fitur yang ada harus diuji untuk memastikan bahwa perubahan sistem tidak berdampak pada fitur yang ada> • <Pengujian End-to-end>
Analisis Dampak Pengujian | <Sebutkan faktor-faktor apa saja yang dapat memengaruhi cakupan dan aktivitas pengujian dalam hal ketergantungan antarmuka, batasan/kendala pengujian, dll. Berikut ini dapat digunakan sebagai masukan untuk melakukan analisis dampak • Setiap Perubahan pada unit, integrasi, sistem, dan kasus uji penerimaan yang ada yang harus dimodifikasi atau dihapus • Kriteria fungsi apa saja yang harus diuji • Kriteria kinerja apa saja yang harus diuji • Kriteria Keamanan apa saja yang harus diuji • Kriteria Regresi apa saja yang harus diuji • Data uji spesifik apa pun yang diperlukan>
Kriteria Keberhasilan Pengujian | <Pengujian dianggap dan diakui untuk diterima sebagai sukses dengan pengujian end-to-end. Semua transaksi on-line yang dilakukan harus tercermin dengan benar dan akurat dalam laporan batch masing-masing. Hasilnya harus diverifikasi dan dikonfirmasi oleh pengguna yang berwenang>
Penguji Terlibat | Nama | Area Tanggung Jawab
| Hsu Lynn | Pending transaction
1) Disiapkan Oleh Tester
___________Signed___________________________________
Nama : Pang Hsu Lynn
Dept : Silverlake
Tanggal : 14th June 2023
2) Direview dan Diverifikasi oleh:
Technical Team Leader |  |  | QAT Team Leader
______________________________________________ |  |  | ______________________________________________
Nama : |  |  | Nama :
Dept : |  |  | Dept :
Tanggal : |  |  | Tanggal :
Note:
*** Jika melibatkan QAT sebagai Tester

## Test Case iOS
Pengujian Script and Log
Nama Proyek: |  |  | VCC Riwayat Transaksi Pending Transaksi |  |  |  |  | Diuji oleh: | Hsu Lynn |  |  |  |  | UAT | Indonesia
[8 empty] | Tanggal Diuji : | 12/06/2023 - 13/06/2023 |  |  |  | Desktop/ Notebook | SIT | English
No SR : | [7 empty] | Direview oleh : | Daniel |  |  |  | IOS Device | Unit
Nomor Versi Spesifikasi Uji: |  |  | 1.0 |  |  |  |  | Tanggal Direview: | 2023-06-14 |  |  |  | Android Device
Environment Pengujian: | [7 empty] | Disetujui oleh :
Jenis Pengujian: | [7 empty] | Tanggal Disetujui:
Nama Modul | Scenario ID | Test Case ID | Langkah-langkah Pengujijan |  | Test Data | Hasil yang Diharapkan | Hasil Sebenarnya | Gambar Hasil | Pass/Fail (P/F) | Tanggal Dieksekusi | Pengujian Dilaksanakan oleh (Nama) | Catatan
Normal Testing
| Having pending transaction data and treats transaction history (using new app) | 1 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | uatvcc051 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details (with treats) |  | P | 12/06/2023 | Hsu Lynn | FE will call to treats/customerTransactionHistoryV2 to get old BE response { "responseCode" : "00", "descErrorCodeEN" : "SUCCEED", "responseData" : { "treatsCustomerTransactionHistoryList" : [ { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "CONVERTED", "transaction_id" : "6563", "authorization_code" : "TES499", "treats" : { "treats_type" : "POINT", "treats_value" : 13 }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 125000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "125000", "authcode" : "TES499", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6579", "authorization_code" : "TEST01", "treats" : { }, "merchant_name" : "SP ASURANSI", "transaction_amount" : 150000 }, "ccTransCurr" : null, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6565", "authorization_code" : "TES499", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 750000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "750000", "authcode" : "TES499", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6566", "authorization_code" : "TES158", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 500000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "500000", "authcode" : "TES158", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6567", "authorization_code" : "TES258", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 181345 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "181345", "authcode" : "TES258", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6568", "authorization_code" : "TES411", "treats" : { }, "merchant_name" : "RETAIL", "transaction_amount" : 80000 }, "ccTransCurr" : null, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 1020000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6569", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "1020000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6570", "authorization_code" : "TES411", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 1000000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "1000000", "authcode" : "TES411", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6571", "authorization_code" : "TES384", "treats" : { }, "merchant_name" : "TELKOM AUTO DEBET ", "transaction_amount" : 250000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "TES384", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TELKOM AUTO DEBET JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6572", "authorization_code" : "TES110", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 50000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "50000", "authcode" : "TES110", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6573", "authorization_code" : "TES110", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 50000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "50000", "authcode" : "TES110", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6574", "authorization_code" : "TES110", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 50000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "50000", "authcode" : "TES110", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 250000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6575", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 250000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6576", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 250000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6577", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6578", "authorization_code" : "TES334", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 800000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "800000", "authcode" : "TES334", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6564", "authorization_code" : "TES499", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 750000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "750000", "authcode" : "TES499", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "C", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "100000", "authcode" : "TES335", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "MAESTRO(MDS) JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "6000", "authcode" : "00", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "CASH ADVANCE PERCENT FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "200000", "authcode" : "TES336", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "MAESTRO(MDS) JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "12000", "authcode" : "00", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "CASH ADVANCE PERCENT FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "200000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "MAESTRO(MDS) JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "12000", "authcode" : "00", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "CASH ADVANCE PERCENT FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "500000", "authcode" : "TES431", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "X BILL PLN JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "80000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "RETAIL", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "1000055", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "C", "transactiondate" : "05092022", "transactiondescription" : "DESKRIPSI LOYALTY", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "100000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "A7 ANNUAL FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "100000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "C", "transactiondate" : "05092022", "transactiondescription" : "A7 ANNUAL FEE REV", "forextransactionamount" : "0.00" }, "maxLimit" : 0 } ], "pendingTransactionList" : [ { "transactionamount" : "+40000.00", "effectivedate" : "050922", "transactiondescription" : "LODGING", "source" : "000001", "days" : "03", "authcode" : "000110" } ] }, "descErrorCode" : "SUKSES" }
| Having pending transaction data and transaction history (using new app) | 2 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | UATvcc030 -5520 0802 4893 7007 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details |  | P | 12/06/2023 | Hsu Lynn | FE will call to /getCardHistory to get BE response { "responseCode" : "00", "descErrorCodeEN" : "SUCCEED", "responseData" : { "creditCardHistory" : [ ], "pendingTranxList" : [ { "transactionamount" : "+525.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00004" }, { "transactionamount" : "+13000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00005" }, { "transactionamount" : "+15000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00007" }, { "transactionamount" : "+14000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00008" }, { "transactionamount" : "+13000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00009" } ] }, "descErrorCode" : "SUKSES" }
Negative Testing
| Don’t have pending transaction data but have treats transaction history (using new app) | 1 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | NA | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) | NA | NA | 22/03/2023 |  | FE will call to treats/customerTransactionHistoryv2 to get new BE response note: there is no user profile to test on this scenario
| Don’t have pending transaction data but have transaction history (using new app) | 2 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | Uatvcc010 - 3562 8560 2653 2001 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details |  | P | 22/03/2023 | Hsu Lynn | FE will call to /getCardHistory to get BE response { "responseCode" : "00", "descErrorCodeEN" : "SUCCEED", "responseData" : { "creditCardHistory" : [ { "postingdate" : "26082022", "transactionamount" : "330000", "authcode" : "051445", "forextransactioncurrency" : "360", "statmentdate" : "00000000", "transactiontype" : "D", "transactiondate" : "25082022", "transactiondescription" : "BINTAN LUMBA-LUMBA INN TJG PINANG ID", "forextransactionamount" : "330000.00" }, { "postingdate" : "21082022", "transactionamount" : "5000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "00000000", "transactiontype" : "D", "transactiondate" : "19082022", "transactiondescription" : "XA BIAYA NOTIFIKASI", "forextransactionamount" : "0.00" } ], "pendingTranxList" : [ ] }, "descErrorCode" : "SUKSES" }
| Having pending transaction data and treats transaction history (using old app) | 3 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | uatvcc051 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) |  | P | 2023-06-12 | Hsu Lynn | FE will call to treats/customerTransactionHistory to get old BE response { "responseCode" : "00", "descErrorCodeEN" : "SUCCEED", "responseData" : [ { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "CONVERTED", "transaction_id" : "6563", "authorization_code" : "TES499", "treats" : { "treats_type" : "POINT", "treats_value" : 13 }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 125000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "125000", "authcode" : "TES499", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6579", "authorization_code" : "TEST01", "treats" : { }, "merchant_name" : "SP ASURANSI", "transaction_amount" : 150000 }, "ccTransCurr" : null, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6565", "authorization_code" : "TES499", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 750000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "750000", "authcode" : "TES499", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6566", "authorization_code" : "TES158", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 500000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "500000", "authcode" : "TES158", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6567", "authorization_code" : "TES258", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 181345 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "181345", "authcode" : "TES258", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6568", "authorization_code" : "TES411", "treats" : { }, "merchant_name" : "RETAIL", "transaction_amount" : 80000 }, "ccTransCurr" : null, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 1020000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6569", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "1020000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6570", "authorization_code" : "TES411", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 1000000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "1000000", "authcode" : "TES411", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6571", "authorization_code" : "TES384", "treats" : { }, "merchant_name" : "TELKOM AUTO DEBET ", "transaction_amount" : 250000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "TES384", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TELKOM AUTO DEBET JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6572", "authorization_code" : "TES110", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 50000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "50000", "authcode" : "TES110", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6573", "authorization_code" : "TES110", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 50000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "50000", "authcode" : "TES110", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6574", "authorization_code" : "TES110", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 50000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "50000", "authcode" : "TES110", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 250000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6575", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 250000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6576", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_amount" : 250000, "merchant_name" : "TEST GENERIK ", "transaction_id" : "6577", "treats" : { }, "conversion_status" : "NOT CONVERTED", "transaction_date" : "2022-09-05" }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "250000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6578", "authorization_code" : "TES334", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 800000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "800000", "authcode" : "TES334", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : { "transaction_date" : "2022-09-05", "conversion_status" : "NOT CONVERTED", "transaction_id" : "6564", "authorization_code" : "TES499", "treats" : { }, "merchant_name" : "TEST GENERIK ", "transaction_amount" : 750000 }, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "750000", "authcode" : "TES499", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "C", "transactiondate" : "05092022", "transactiondescription" : "TEST GENERIK JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "100000", "authcode" : "TES335", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "MAESTRO(MDS) JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "6000", "authcode" : "00", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "CASH ADVANCE PERCENT FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "200000", "authcode" : "TES336", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "MAESTRO(MDS) JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "12000", "authcode" : "00", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "CASH ADVANCE PERCENT FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "200000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "MAESTRO(MDS) JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "12000", "authcode" : "00", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "CASH ADVANCE PERCENT FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "500000", "authcode" : "TES431", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "X BILL PLN JAKARTA ID", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "80000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "RETAIL", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "1000055", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "C", "transactiondate" : "05092022", "transactiondescription" : "DESKRIPSI LOYALTY", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "100000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "D", "transactiondate" : "05092022", "transactiondescription" : "A7 ANNUAL FEE", "forextransactionamount" : "0.00" }, "maxLimit" : 0 }, { "customerTransactionHistory" : null, "ccTransCurr" : { "postingdate" : "05092022", "transactionamount" : "100000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "05092022", "transactiontype" : "C", "transactiondate" : "05092022", "transactiondescription" : "A7 ANNUAL FEE REV", "forextransactionamount" : "0.00" }, "maxLimit" : 0 } ], "descErrorCode" : "SUKSES" }
| Having pending transaction data and transaction history (using old app) | 4 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | UATvcc030 -5520 0802 4893 7007 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details |  | P | 2023-06-12 | Hsu Lynn | FE will call to /getCardHistory to get BE response { "responseCode" : "00", "descErrorCodeEN" : "SUCCEED", "responseData" : { "creditCardHistory" : [ ], "pendingTranxList" : [ { "transactionamount" : "+525.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00004" }, { "transactionamount" : "+13000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00005" }, { "transactionamount" : "+15000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00007" }, { "transactionamount" : "+14000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00008" }, { "transactionamount" : "+13000.00", "effectivedate" : "040922", "transactiondescription" : "HOTEL/MOTEL", "source" : "000001", "days" : "02", "authcode" : "H00009" } ] }, "descErrorCode" : "SUKSES" }
| Don’t have pending transaction data but have treats transaction history (using old app) | 5 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | NA | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) |  | NA | 2023-06-12 |  | FE will call to treats/customerTransactionHistory to get old BE response Note: there is no user profile that can be used to test this scenario
| Don’t have pending transaction data but have transaction history (using old app) | 6 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | Uatvcc010 - 3562 8560 2653 2001 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details |  | P | 2023-06-12 | Hsu Lynn | FE will call to /getCardHistory to get BE response { "responseCode" : "00", "descErrorCodeEN" : "SUCCEED", "responseData" : { "creditCardHistory" : [ { "postingdate" : "26082022", "transactionamount" : "330000", "authcode" : "051445", "forextransactioncurrency" : "360", "statmentdate" : "00000000", "transactiontype" : "D", "transactiondate" : "25082022", "transactiondescription" : "BINTAN LUMBA-LUMBA INN TJG PINANG ID", "forextransactionamount" : "330000.00" }, { "postingdate" : "21082022", "transactionamount" : "5000", "authcode" : "", "forextransactioncurrency" : "000", "statmentdate" : "00000000", "transactiontype" : "D", "transactiondate" : "19082022", "transactiondescription" : "XA BIAYA NOTIFIKASI", "forextransactionamount" : "0.00" } ], "pendingTranxList" : [ ] }, "descErrorCode" : "SUKSES" }
Catatan: - Pengujian harus mencakup fitur utama atau perubahan yang ditentukan dalam FSD dan TSD. - Pengujian harus mencakup semua aktivitas dan proses yang relevan dengan fitur atau perubahan utama. - Setiap aktivitas atau proses yang tidak dapat dimasukkan dalam pengujian harus diumumkan. Rencana mitigasi yang memadai harus dijelaskan dan disetujui oleh Project (Business) Owner / System Owner

## Test Case Android
Pengujian Script and Log
Nama Proyek: |  |  | VCC Riwayat Transaksi Pending Transaksi |  |  |  |  | Diuji oleh: | Hsu Lynn |  |  |  |  | UAT | Indonesia
[8 empty] | Tanggal Diuji : | 12/06/2023 - 13/06/2023 |  |  |  | Desktop/ Notebook | SIT | English
No SR : | [7 empty] | Direview oleh : | Daniel |  |  |  | IOS Device | Unit
Nomor Versi Spesifikasi Uji: |  |  | 1.0 |  |  |  |  | Tanggal Direview: | 2023-06-14 |  |  |  | Android Device
Environment Pengujian: | [7 empty] | Disetujui oleh :
Jenis Pengujian: | [7 empty] | Tanggal Disetujui:
Nama Modul | Scenario ID | Test Case ID | Langkah-langkah Pengujijan |  | Test Data | Hasil yang Diharapkan | Hasil Sebenarnya | Gambar Hasil | Pass/Fail (P/F) | Tanggal Dieksekusi | Pengujian Dilaksanakan oleh (Nama) | Catatan
Normal Testing
| Having pending transaction data and treats transaction history (using new app) | 1 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | uatvcc051 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details (with treats) |  | P | 22/03/2023 | Hsu Lynn | FE will call to treats/customerTransactionHistoryV2 to get old BE response { "responseCode": "00", "descErrorCode": "SUKSES", "descErrorCodeEN": "SUCCEED", "responseData": { "treatsCustomerTransactionHistoryList": [ { "customerTransactionHistory": { "transaction_id": "6563", "authorization_code": "TES499", "merchant_name": "TEST GENERIK ", "transaction_amount": 125000, "transaction_date": "2022-09-05", "conversion_status": "CONVERTED", "treats": { "treats_type": "POINT", "treats_value": 13 } }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "125000", "statmentdate": "05092022", "authcode": "TES499" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6579", "authorization_code": "TEST01", "merchant_name": "SP ASURANSI", "transaction_amount": 150000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": null, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6565", "authorization_code": "TES499", "merchant_name": "TEST GENERIK ", "transaction_amount": 750000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "750000", "statmentdate": "05092022", "authcode": "TES499" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6566", "authorization_code": "TES158", "merchant_name": "TEST GENERIK ", "transaction_amount": 500000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "500000", "statmentdate": "05092022", "authcode": "TES158" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6567", "authorization_code": "TES258", "merchant_name": "TEST GENERIK ", "transaction_amount": 181345, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "181345", "statmentdate": "05092022", "authcode": "TES258" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6568", "authorization_code": "TES411", "merchant_name": "RETAIL", "transaction_amount": 80000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": null, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6569", "merchant_name": "TEST GENERIK ", "transaction_amount": 1020000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "1020000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6570", "authorization_code": "TES411", "merchant_name": "TEST GENERIK ", "transaction_amount": 1000000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "1000000", "statmentdate": "05092022", "authcode": "TES411" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6571", "authorization_code": "TES384", "merchant_name": "TELKOM AUTO DEBET ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TELKOM AUTO DEBET JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "TES384" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6572", "authorization_code": "TES110", "merchant_name": "TEST GENERIK ", "transaction_amount": 50000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "50000", "statmentdate": "05092022", "authcode": "TES110" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6573", "authorization_code": "TES110", "merchant_name": "TEST GENERIK ", "transaction_amount": 50000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "50000", "statmentdate": "05092022", "authcode": "TES110" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6574", "authorization_code": "TES110", "merchant_name": "TEST GENERIK ", "transaction_amount": 50000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "50000", "statmentdate": "05092022", "authcode": "TES110" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6575", "merchant_name": "TEST GENERIK ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6576", "merchant_name": "TEST GENERIK ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6577", "merchant_name": "TEST GENERIK ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6578", "authorization_code": "TES334", "merchant_name": "TEST GENERIK ", "transaction_amount": 800000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "800000", "statmentdate": "05092022", "authcode": "TES334" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6564", "authorization_code": "TES499", "merchant_name": "TEST GENERIK ", "transaction_amount": 750000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "C", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "750000", "statmentdate": "05092022", "authcode": "TES499" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "MAESTRO(MDS) JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "100000", "statmentdate": "05092022", "authcode": "TES335" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "CASH ADVANCE PERCENT FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "6000", "statmentdate": "05092022", "authcode": "00" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "MAESTRO(MDS) JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "200000", "statmentdate": "05092022", "authcode": "TES336" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "CASH ADVANCE PERCENT FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "12000", "statmentdate": "05092022", "authcode": "00" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "MAESTRO(MDS) JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "200000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "CASH ADVANCE PERCENT FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "12000", "statmentdate": "05092022", "authcode": "00" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "X BILL PLN JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "500000", "statmentdate": "05092022", "authcode": "TES431" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "RETAIL", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "80000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "DESKRIPSI LOYALTY", "postingdate": "05092022", "transactiontype": "C", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "1000055", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "A7 ANNUAL FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "100000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "A7 ANNUAL FEE REV", "postingdate": "05092022", "transactiontype": "C", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "100000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 } ], "pendingTransactionList": [ { "transactionamount": "+40000.00", "authcode": "000110", "days": "03", "effectivedate": "050922", "source": "000001", "transactiondescription": "LODGING" } ] } }
| Having pending transaction data and transaction history (using new app) | 2 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | UATvcc030 -5520 0802 4893 7007 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Pending Transaction and Transaction History details |  | P | 22/03/2023 | Hsu Lynn | FE will call to /getCardHistory to get BE response { "responseCode": "00", "descErrorCode": "SUKSES", "descErrorCodeEN": "SUCCEED", "responseData": { "creditCardHistory": [], "pendingTranxList": [ { "transactionamount": "+525.00", "authcode": "H00004", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+13000.00", "authcode": "H00005", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+15000.00", "authcode": "H00007", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+14000.00", "authcode": "H00008", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+13000.00", "authcode": "H00009", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" } ] } }
Negative Testing
| Don’t have pending transaction data but have treats transaction history (using new app) | 1 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | NA | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) |  | NA | 22/03/2023 |  | FE will call to treats/customerTransactionHistoryv2 to get new BE response Note: there is no user profile to be used to test this scenario
| Don’t have pending transaction data but have transaction history (using new app) | 2 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | Uatvcc010 - 3562 8560 2653 2001 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details |  | P | 2023-06-12 | Hsu Lynn | FE will call to getCardHistory to get BE response { "responseCode": "00", "descErrorCode": "SUKSES", "descErrorCodeEN": "SUCCEED", "responseData": { "creditCardHistory": [ { "transactiondate": "25082022", "transactiondescription": "BINTAN LUMBA-LUMBA INN TJG PINANG ID", "postingdate": "26082022", "transactiontype": "D", "forextransactionamount": "330000.00", "forextransactioncurrency": "360", "transactionamount": "330000", "statmentdate": "00000000", "authcode": "051445" }, { "transactiondate": "19082022", "transactiondescription": "XA BIAYA NOTIFIKASI", "postingdate": "21082022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "5000", "statmentdate": "00000000", "authcode": "" } ], "pendingTranxList": [] } }
| Having pending transaction data and treats transaction history (using old app) | 3 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | uatvcc051 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) |  | P | 2023-06-12 | Hsu Lynn | FE will call to treats/customerTransactionHistory to get old BE response { "responseCode": "00", "descErrorCode": "SUKSES", "descErrorCodeEN": "SUCCEED", "responseData": [ { "customerTransactionHistory": { "transaction_id": "6563", "authorization_code": "TES499", "merchant_name": "TEST GENERIK ", "transaction_amount": 125000, "transaction_date": "2022-09-05", "conversion_status": "CONVERTED", "treats": { "treats_type": "POINT", "treats_value": 13 } }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "125000", "statmentdate": "05092022", "authcode": "TES499" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6579", "authorization_code": "TEST01", "merchant_name": "SP ASURANSI", "transaction_amount": 150000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": null, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6565", "authorization_code": "TES499", "merchant_name": "TEST GENERIK ", "transaction_amount": 750000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "750000", "statmentdate": "05092022", "authcode": "TES499" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6566", "authorization_code": "TES158", "merchant_name": "TEST GENERIK ", "transaction_amount": 500000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "500000", "statmentdate": "05092022", "authcode": "TES158" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6567", "authorization_code": "TES258", "merchant_name": "TEST GENERIK ", "transaction_amount": 181345, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "181345", "statmentdate": "05092022", "authcode": "TES258" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6568", "authorization_code": "TES411", "merchant_name": "RETAIL", "transaction_amount": 80000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": null, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6569", "merchant_name": "TEST GENERIK ", "transaction_amount": 1020000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "1020000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6570", "authorization_code": "TES411", "merchant_name": "TEST GENERIK ", "transaction_amount": 1000000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "1000000", "statmentdate": "05092022", "authcode": "TES411" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6571", "authorization_code": "TES384", "merchant_name": "TELKOM AUTO DEBET ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TELKOM AUTO DEBET JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "TES384" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6572", "authorization_code": "TES110", "merchant_name": "TEST GENERIK ", "transaction_amount": 50000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "50000", "statmentdate": "05092022", "authcode": "TES110" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6573", "authorization_code": "TES110", "merchant_name": "TEST GENERIK ", "transaction_amount": 50000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "50000", "statmentdate": "05092022", "authcode": "TES110" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6574", "authorization_code": "TES110", "merchant_name": "TEST GENERIK ", "transaction_amount": 50000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "50000", "statmentdate": "05092022", "authcode": "TES110" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6575", "merchant_name": "TEST GENERIK ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6576", "merchant_name": "TEST GENERIK ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6577", "merchant_name": "TEST GENERIK ", "transaction_amount": 250000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "250000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6578", "authorization_code": "TES334", "merchant_name": "TEST GENERIK ", "transaction_amount": 800000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "800000", "statmentdate": "05092022", "authcode": "TES334" }, "maxLimit": 0 }, { "customerTransactionHistory": { "transaction_id": "6564", "authorization_code": "TES499", "merchant_name": "TEST GENERIK ", "transaction_amount": 750000, "transaction_date": "2022-09-05", "conversion_status": "NOT CONVERTED", "treats": {} }, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "TEST GENERIK JAKARTA ID", "postingdate": "05092022", "transactiontype": "C", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "750000", "statmentdate": "05092022", "authcode": "TES499" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "MAESTRO(MDS) JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "100000", "statmentdate": "05092022", "authcode": "TES335" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "CASH ADVANCE PERCENT FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "6000", "statmentdate": "05092022", "authcode": "00" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "MAESTRO(MDS) JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "200000", "statmentdate": "05092022", "authcode": "TES336" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "CASH ADVANCE PERCENT FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "12000", "statmentdate": "05092022", "authcode": "00" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "MAESTRO(MDS) JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "200000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "CASH ADVANCE PERCENT FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "12000", "statmentdate": "05092022", "authcode": "00" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "X BILL PLN JAKARTA ID", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "500000", "statmentdate": "05092022", "authcode": "TES431" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "RETAIL", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "80000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "DESKRIPSI LOYALTY", "postingdate": "05092022", "transactiontype": "C", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "1000055", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "A7 ANNUAL FEE", "postingdate": "05092022", "transactiontype": "D", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "100000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 }, { "customerTransactionHistory": null, "ccTransCurr": { "transactiondate": "05092022", "transactiondescription": "A7 ANNUAL FEE REV", "postingdate": "05092022", "transactiontype": "C", "forextransactionamount": "0.00", "forextransactioncurrency": "000", "transactionamount": "100000", "statmentdate": "05092022", "authcode": "" }, "maxLimit": 0 } ] }
| Having pending transaction data and transaction history (using old app) | 4 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | UATvcc030 -5520 0802 4893 7007 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details |  | P | 2023-06-12 | Hsu Lynn | FE will call to /getCardHistory to get BE response { "responseCode": "00", "descErrorCode": "SUKSES", "descErrorCodeEN": "SUCCEED", "responseData": { "creditCardHistory": [], "pendingTranxList": [ { "transactionamount": "+525.00", "authcode": "H00004", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+13000.00", "authcode": "H00005", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+15000.00", "authcode": "H00007", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+14000.00", "authcode": "H00008", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" }, { "transactionamount": "+13000.00", "authcode": "H00009", "days": "02", "effectivedate": "040922", "source": "000001", "transactiondescription": "HOTEL/MOTEL" } ] } }
| Don’t have pending transaction data but have treats transaction history (using old app) | 5 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | NA | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details (with treats) |  | NA | 2023-06-12 |  | FE will call to treats/customerTransactionHistory to get old BE response Note: there is no user profile to be used to test this scenario
| Don’t have pending transaction data but have transaction history (using old app) | 6 | 1 | 1. Login M2U app 2. Navigate to Icon Credit Card 3. Click "Riwayat Transaksi" | Uatvcc010 - 3562 8560 2653 2001 | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details | 1. Able to login 2, Able to view Credit Card data 3. Able to view Transaction History details |  | P | 2023-03-12 | Hsu Lynn | FE will call to /getCardHistory to get BE response { "responseCode": "00", "descErrorCode": "SUKSES", "descErrorCodeEN": "SUCCEED", "responseData": { "creditCardHistory": [ { "authcode": "", "postingdate": "30082022", "transactiondate": "30082022", "statmentdate": "00000000", "transactionamount": "666667", "transactiontype": "D", "transactiondescription": "XCASH TELESALES :002/006", "forextransactionamount": "6666.67", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "29082022", "transactiondate": "29082022", "statmentdate": "00000000", "transactionamount": "1000000", "transactiontype": "D", "transactiondescription": "XCASH TELESALES :001/006", "forextransactionamount": "10000.00", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "29082022", "transactiondate": "29082022", "statmentdate": "00000000", "transactionamount": "1500000", "transactiontype": "D", "transactiondescription": "XCASH TELESALES :002/006", "forextransactionamount": "15000.00", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "29082022", "transactiondate": "29082022", "statmentdate": "00000000", "transactionamount": "2166667", "transactiontype": "D", "transactiondescription": "XCASH TELESALES :001/006", "forextransactionamount": "21666.67", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "29082022", "transactiondate": "29082022", "statmentdate": "00000000", "transactionamount": "3166667", "transactiontype": "D", "transactiondescription": "XCASH TELESALES :002/006", "forextransactionamount": "31666.67", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "28082022", "transactiondate": "27082022", "statmentdate": "00000000", "transactionamount": "20000", "transactiontype": "D", "transactiondescription": "XA CONVERSION XCASH", "forextransactionamount": "0.00", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "28082022", "transactiondate": "27082022", "statmentdate": "00000000", "transactionamount": "20000", "transactiontype": "D", "transactiondescription": "XA CONVERSION XCASH", "forextransactionamount": "0.00", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "28082022", "transactiondate": "27082022", "statmentdate": "00000000", "transactionamount": "154000", "transactiontype": "D", "transactiondescription": "XA ADM FEE XCASH", "forextransactionamount": "0.00", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "28082022", "transactiondate": "27082022", "statmentdate": "00000000", "transactionamount": "346500", "transactiontype": "D", "transactiondescription": "XA ADM FEE XCASH", "forextransactionamount": "0.00", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "21082022", "transactiondate": "19082022", "statmentdate": "00000000", "transactionamount": "5000", "transactiontype": "D", "transactiondescription": "XA BIAYA NOTIFIKASI", "forextransactionamount": "0.00", "forextransactioncurrency": "000" }, { "authcode": "", "postingdate": "21082022", "transactiondate": "19082022", "statmentdate": "00000000", "transactionamount": "15000", "transactiontype": "D", "transactiondescription": "EB FEE BILLING STATEMENT", "forextransactionamount": "0.00", "forextransactioncurrency": "000" } ] } }
Catatan: - Pengujian harus mencakup fitur utama atau perubahan yang ditentukan dalam FSD dan TSD. - Pengujian harus mencakup semua aktivitas dan proses yang relevan dengan fitur atau perubahan utama. - Setiap aktivitas atau proses yang tidak dapat dimasukkan dalam pengujian harus diumumkan. Rencana mitigasi yang memadai harus dijelaskan dan disetujui oleh Project (Business) Owner / System Owner

## Defect Log
Defect Log
Nama Proyek: |  |  |  |  | Dibuat Oleh dan Sign Off: |  |  | Paraf | Desktop/ Notebook | UAT | Indonesia
[5 empty] | Dibuat pada tanggal: |  |  |  | IOS Device | SIT | English
SR No. |  |  |  |  | Direview Oleh dan Sign Off: |  |  | Paraf | Android Device | Unit
Nomor Versi Spesifikasi Pengujian: |  |  |  |  | Direview pada tanggal:
Environment Pengujian: |  |  |  |  | Disetujui oleh dan Sign Off: |  |  | Paraf
Jenis Pengujian: |  |  |  |  | Disetujui pada tanggal:
No Tiket | Test Case ID | Nama Modul | Deskripsi | Severity (Minor/Major/Critical) | Resolusi | Creator | Owner | Attachment

## Sign Off
System Integration Testing (SIT) Sign Off
No. SR / No. Tiket | :
Nama Perubahan | : Pending transaction
Jenis Pengujian | : SIT
Durasi Pengujian | : 12/06/2023 - 13/06/2023
Hash Check | : □ Yes | □ No
DIBUAT | Nama | Unit Kerja | Tanda Tangan | Tanggal
Technical Team
DIREVIEW | Nama | Unit Kerja | Tanda Tangan | Tanggal
Technical TL
IT PM
DISETUJUI | Nama | Unit Kerja | Tanda Tangan | Tanggal
Application Owner
DIVERIFIKASI | Nama | Unit Kerja | Tanda Tangan | Tanggal
IT QCA