## Summary APK
No | Severity | App | Findings | PIC | Recommendation from pentester | Solution | Remediaton date | Remarks
4.2.1 | Low | Business Banking | 4.2.1 Android: Weak Root Detection Rooting is the process of gaining administrative or privileged access to the Android OS. Without root detection, attackers or malware may access sensitive information stored on the device. | Silverlake | Developers should employ better methods to detect whether an app is running on a rooted device. | Implement jailbreak detection. | July 29, 2025 4 mandays | Details in "Business ocbc" sheet - pen-tester successfully bypassed root detection
4.2.2 | Medium | Business Banking | 4.2.2 Android: Certificate files hardcoded inside the app SSL Pinning is a security mechanism used to prevent man-in-the-middle attacks by validating the certificate of a trusted server during the SSL handshake. Developers store a list of trusted certificates within the app and use them to compare against the server certificate. Improper SSL Pinning implementation can make the app vulnerable to man-in-the-middle attacks if the certificate list is hardcoded and outdated. | Silverlake | Developers are advised to add obfuscation to make decompilation difficult and to use public keys as variables to make reverse engineering difficult for attackers. | Implement hashed public key instead of loading real cert. | July 29, 2025 5 mandays | Details in "Business ocbc" sheet - pen-tester successfully bypassed root detection
4.2.3 | Low | Business Banking | 4.2.3 iOS: No Jailbreak Detection Jailbreaking is the process of gaining administrative or privileged access to the iOS OS. Without jailbreak detection, attackers may access sensitive information from the app running on the device. | Silverlake | Developers must detect whether the application is running on a jailbroken device. | Implement jailbreak detection. | July 29, 2025 4 mandays | Details in "Business ocbc" sheet - no jailbreak detection in code
4.2.4 | Medium | Business Banking | 4.2.4 iOS: Certificate files hardcoded inside the app Same as Android – developers embed a list of trusted certificates inside the app and use it to validate server certificates. If not properly implemented, this can leave the app vulnerable to man-in-the-middle attacks. | Silverlake | Developers are advised to add obfuscation to make decompilation difficult and to use public keys as variables, making it difficult for attackers to reverse engineer. | Implement hashed public key instead of loading real cert. | July 29, 2025 5 mandays | Details in "Business ocbc" sheet - pen-tester successfully bypassed root detection
4.2.5 | Medium | Business Banking | 4.2.5 iOS: Weak SSL Pinning During testing on iOS apps, the tester found that the app does not implement SSL Pinning. Without SSL Pinning, attackers can intercept and modify data transmitted between the app and server using invalid certificates, increasing the risk of data tampering. | Silverlake | Developers should implement SSL Pinning. | Implement hashed public key to pin the cert. | July 29, 2025 4 mandays | Details in "Business ocbc" sheet - Currently we are using MTLS so it does not require SSL Pinning on the client side. SSL pinning should be taken out
4.2.6 | Medium | Bussines Banking | 4.2.6 API: User Enumeration through Error Messages Error messages in an application can provide valid and invalid username information. This information can potentially provide attackers with information for further attacks. This information allows attackers to perform brute-force attacks on the application. | Silverlake | It is recommended to provide the same information in the error message so that it does not display whether the username is valid or not. | Implement access control by session id to match username. | July 29, 2025 5 mandays | Details in "Business ocbc" sheet - From FE the error message already general
4.2.7 | High | Business Banking | 4.2.7 API: Insecure Direct Object Reference Vulnerability (IDOR) The IDOR vulnerability occurs when an app exposes internal object references without access control. This allows attackers to access data by manipulating input values. If exploited, IDOR may lead to serious business data breaches. | Silverlake | Developers must implement proper access control so that users can only access information or perform actions within a session that are defined by the access rights assigned to that session. | Implement access control by session id to match username. | July 29, 2025 5 mandays | Details in "Business ocbc" sheet - there is broken access control
4.2.8 | Medium | Business Banking | 4.2.8 API: Bypass OTP in Biometric Activation Modification of response parameters in the API allows an attacker to alter values such as item prices, item quantities, and other sensitive data commonly used in business transactions, potentially leading to unauthorized changes being accepted by the server. | Silverlake | It is recommended to re-verify whether the modified data is valid or not. | OTP is invalid, session isn't established at backend. When hacker modifies the status code in response to gain access, firing next web service will be blocked by backend, and instruct frontend back to login screen. | July 29, 2025 5 mandays | Details in "Business ocbc" sheet - the OTP page can be altered

## Bussines ocbc
4.2 | Pen-testers conducting tests on the application version 1.0.42 discovered that the developer had implemented a root detection method using a force-close method, as shown in the screenshots below:
However, using the hide-root method, the Magisk pen-tester successfully bypassed root detection, as shown in the screenshots below:However, using the hide-root method, the Magisk pen-tester successfully bypassed root detection, as shown in the screenshots below:
4.2.2 | However, using the hide-root method, the Magisk pen-tester successfully bypassed root detection, as shown in the screenshots below:However, using the hide-root method, the Magisk pen-tester successfully bypassed root detection, as shown in the screenshots below:
By using the certificate, the pen-tester successfully obtained the certificate password as shown in the screenshot below:
4.2.3 | Pen-testers testing the app version 1.0.38 found that the developer failed to implement jailbreak detection when running the app on a jailbroken device, as shown in the screenshots below:
4.2.4 | A pen tester testing the application version 1.0.38 discovered that the developer had hardcoded the certificate into the application. The following screenshot shows the hardcoded certificate in the application:
4.2.5 | A pen-tester testing the application version 1.0.38 found that the application stores the certificate within the application, allowing it to be used in proxy applications, as shown in the following screenshot:
By using this certificate, the pen-tester can intercept the application, as shown in the screenshot below:
4.2.6 | The pentester discovered that the developer failed to implement error handling during authentication, allowing valid users to be identified through different error messages. Here's a screenshot of what happens when an unregistered username is entered:
Here is a screenshot when the pen-tester enters a valid username but the password is wrong:
Using this information, a pen-tester can perform an enumeration attack and collect a list of valid usernames, as shown in the screenshot below:
4.2.7 | The pen-tester discovered that the developer hadn't implemented proper access controls, allowing the pen-tester to view other users' data. The following screenshot shows the user Fathul Ramadhan:
Here is when the pen-tester accesses another user, it can be seen that the username is Dafelina Ramadhan:
4.2.8 | The pentester discovered that the developer had improperly implemented the OTP verification process in the Biometric Activation feature, allowing for OTP bypass. Here's the initial screen when the pentester requested an OTP:
Then, the pentester entered the wrong OTP, resulting in a response like the screenshot below:
Next, the pentester modifies the response code to 000000, as shown in the screenshot below:
By modifying the response, the application is redirected to the success page, as shown in